## Sheet1
TEST SCENARIO DOCUMENT FOR MONIEPOINT MOBILE APP
Product Name | Moniepoint Personal Banking
IOS version | 16.6
App Version | 1.1.1
Created By | Matachi Ononuju
Creation Date | 2nd September 2023
Approval Date
Moniepoint Account Detail
Account Name | Matachi Ononuju
Account Number | 5358613033

## REPORT ANALYSIS
Test Scenarios | Number of test conducted | Assigned | Status | Priority | Pass | Fail
Download | 3 | yes | Closed | High | 3 | 0
Sign Up | 13 | yes | Pending | High | 10 | 3
Login | 2 | yes | Closed | High | 2 | 0
log-out | 2 | yes | Closed | High | 2 | 0
Home | 22 | yes | Pending | High | 6 | 16
Settings | 8 | Yes | Pending | High | 6 | 2
Cards | 3 | Yes | Pending | High | 3 | 0
Total | 53 |  |  |  | 32 | 21

## Defect Report
Defect Report
Defect ID | Defect Description | Steps to Reproduce | Severity | Created By | Assigned to | Status
TC_2.8 | Undersore was not regarded as a special character for the password creation | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date 9. Click Next 10. Input name 11. Input password | Medium | Matachi | Devs | Open
TC_2.11 | Face verification was accepted with glasses on | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date 9. Click Next 10. Input name 11. Input password 12. Verify face ID with glasses. | High | Matachi | Devs | Open
TC_2.12 | The application crashes. User is sent to a blank screen | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date 9. Select Next 10. Verify face ID 11. Input address 12. Click on next 13. Click on the back button | Critical | Matachi | Devs | Open
TC_5.3 | The wrong bank was selected by the app | 1. Open App 2. Click on Transfer 3. Input account number 4. Select bank | Medium | Matachi | Devs | Open
TC_5.4 | A jason file was downloaded instead of an excel file for standard statment | 1. Open App 2. Click on Transfer 3. Click on the clock icon (History) 4. Click on the download icon 5. Select Standard Statement 6. click next 7. Select range 8. Click Excel 9. Click on next 10. Select Instant download 11. Click export | High | Matachi | Devs | Open
TC_5.5 | A jason file was downloaded instead of a pdf for standard statment | 1. Open App 2. Click on Transfer 3. Click on the clock icon (History) 4. Click on the download icon 5. Select Standard Statement 6. click next 7. Select range 8. Click pdf 9. Click on next 10. Select Instant download 11. Click export | High | Matachi | Devs | Open
TC_5.6 | A jason file was downloaded instead of an excel file for extended statement | 1. Open App 2. Click on Transfer 3. Click on the clock icon (History) 4. Click on the download icon 5. Select Extentended Statement 6. click next 7. Select range 8. Click Excel 9. Click on next 10. Select Instant download 11. Click export | High | Matachi | Devs | Open
TC_5.7 | A jason file was downloaded instead of a pdf for extended statement | 1. Open App 2. Click on Transfer 3. Click on the clock icon (History) 4. Click on the download icon 5. Select Extentended Statement 6. click next 7. Select range 8. Click pdf 9. Click on next 10. Select Instant download 11. Click export | High | Matachi | Devs | Open
TC_5.8 | Money in and Money Out isn't displaying properly on the Home screen | 1. Open app 2. Scroll down | High | Matachi | Devs | Open
TC_5.10 | The service provider and Moniepoint account were not displayed when trying to purchase airtime | 1. Open App 2. Click on Top-Up 3. add phone number 4. Click proceed | Medium | Matachi | Devs | Open
TC_5.11 | The service provider was not displayed in Beneficiary Details | 1. Open App 2. Click on Top-Up 3. add phone number 4. Click proceed 5. Input amount 6. Click Proceed | Medium | Matachi | Devs | Open
TC_5.12 | The application requested the users pin but the input pin field was displayed in red | 1. Open App 2. Click on Top-Up 3. add phone number 4. Click proceed 5. Input amount 6. Click Proceed | Low | Matachi | Devs | Open
TC_5.13 | The app selected MTN as the network provider | 1. Open App 2. Click on Top-Up 3. add phone number | Low | Matachi | Devs | Open
TC_5.15 | Data puchased without being saved to beneficiary was saved to beneficiary | 1. Open App 2. Click on Top-Up 3. Selecetd Data 4. add phone number 5. Click proceed 6. Input amount 7. Click Proceed 8. Click Proceed 9. Input pin 10. Click Confrim | Medium | Matachi | Devs | Open
TC_5.16 | Data puchased that was saved to beneficiary was not saved to beneficiaries of data | 1. Open App 2. Click on Top-Up 3. Selecetd Data 4. add phone number 5. Select add beneficiarie 6. Input beneficiary name 7. Click proceed 8. Input amount 9. Click Proceed 10. Click Proceed 11. Input pin 12. Click Confrim | Medium | Matachi | Devs | Open
TC_5.17 | The application requested the users pin but the input pin field was displayed in red | 1. Open App 2. Click on Top-Up 3. Select Data 4. add phone number 5. Click proceed 6. Input amount 7. Click Proceed | low | Matachi | Devs | Open
TC_5.19 | No data was displayed in the document downloaded from data history | 1. Open App 2. Click on Top-Up 3. on Clock Icon 4. Select data 5. Click on the download Icon 6. Open File | High | Matachi | Devs | Open
TC_5.20 | "Failed Oops! It seems your history is empty" was displayed when trying to download the history from Airtime purchase | 1. Open App 2. Click on Top-Up 3. on Clock Icon 4. Click on the download icon | Medium | Matachi | Devs | Open
TC_5.21 | A pop up notification was recieved but the number of notifications were not displayed on the notification icon | 1. Open app 2. Make transcation 3. View notification icon | Low | Matachi | Devs | Open
TC_6.6 | Airtime purchase beneficiary only displayed numbers | 1. Open aApp 2. Click on profile picture 3. Click on Beneficiaries | Medium | Matachi | Devs | Open
TC_6.8 | An Error message was displayed "An Unexpected error occured while processing your request. Please try again later" while trying to delete a beneficiary | 1. Open aApp 2. Click on profile picture 3. Click on Beneficiaries 4. Click on Airtime 5. Click on the Bin icon 6. Select Remove | Medium | Matachi | Devs | Open

## Images
Screen Shots of Errors
Money In and Money Out not displaying properly | Data not saved as beneficiary Being displayed as beneficiary |  | No Service provider was displayed in the Airtime purchase Sumarry
The UI input error for Input Transaction Pin in Airtime purchase |  | The UI input error for Input Transaction Pin in Data purchase

## TEST SCENARIOS
TEST SCENARIO APP
Test Scenario ID | Refrences | Test Scenario Description | Priority | Number of Test Cases
TS_01 DOWNLOAD | APP | Validate app installation from App Store | P0 | 3
TS_02 SIGN UP | APP | Validate the Sign Up functionality | P0 | 13
TS_03 LOGIN | APP | Validate the working of login functionality | P0 | 2
TS_04 LOGOUT | APP | Validate the working of logout functionality | P0 | 2
TS_05 HOME | APP | Validate the Functionality of HOME | P0 | 22
TS_06 SETTINGS | APP | Validate the Functionality of SETTINGS | P0 | 8
TS_07 CARDS | APP | Validate the Functionality of CARDS | P0 | 3
TS_08 PAY BILLS | APP | Validate the Functionality of Pay Bils | P0 | N/A

## DOWNLOAD
DOWNLOAD
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result | Actual Result | Results | Comments
TC_1 | TS_1 DOWNLOAD App Store | To verify that the app can be downloaded on app store | An IOS device | 1. Click on link https://apps.apple.com/ng/app/moniepoint-personal-banking/id645275667 2. Select Install 3. Verify identity on app store 4. Open app | None | The app should be downloaded | The app was downloaded | Passed

## SIGN UP
SIGN UP
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result | Actual Result | Results | Comments
TC_2 | TS_02 SIGN UP | To verify the applications reaction when an invalod email is selected | Access To the Mobile App | 1. Open App 2. Select Sign Up | Not applicable |  | As Expected | Passed
TC_2.1 | TS_02 SIGN UP | To verify the applications reaction when a valid email is seleted | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next | Not applicable |  | As Expected | Passed
TC_2.2 | TS_02 SIGN UP | To verify that user recieves OTP | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next | Not applicable | The application should be directed to the BVN verification | As Expected | Passed
TC_2.3 | TS_02 SIGN UP | To verify the applications reaction when an invalid OTP is selected | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next | Not applicable | The OTP should be rejected | As Expected | Passed
TC_2.4 | TS_02 SIGN UP | To verify the applications reaction when an invalid BVN is inputed | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input invalid BVN 7. Input date 8. Click on date | Not applicable |  | As Expected | Passed
TC_2.5 | TS_02 SIGN UP | To verify the applications reaction when a valid BVN is inputed with the wrong date | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input wrong date 8. Click on date | Not applicable |  | As Expected | Passed
TC_2.6 | TS_02 SIGN UP | To verify the applications reaction when a valid BVN is inputed with the correct date | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date | Not applicable | The user should be directed to create a profile | As Expected | Passed
TC_2.7 | TS_02 SIGN UP | To verify the Applications reaction when a user inputs an already taken name | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date 9. Click Next 10. Input already used name | Not applicable | The user should be warned that the name is been used | As Expected | Passed
TC_2.8 | TS_02 SIGN UP Password | To verify the applications reaction when a password with a special character is inputed (_) | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date 9. Click Next 10. Input name 11. Input password | Not applicable | The password filed should accept special characters | Undersore was not regarded as a special character | Failed
TC_2.11 | TS_02 SIGN UP Face verification | To verify that a user can't be verified with glasses on | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date 9. Click Next 10. Input name 11. Input password 12. Verify face ID with glasses. | Account name: MatachI Ononuju | A users face verification should not be accepted with glasses on | Face verification was accepted with glasses on | Failed
TC_2.12 | TS_02 SIGN UP | To verify the applications reaction when the back button is selected during attestation | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date 9. Select Next 10. Verify face ID 11. Input address 12. Click on next 13. Click on the back button | Not applicable |  | The application crashes. User is sent to a blank screen | Failed | The user is required to close the application, the. re-open the application to get back to the attestation page
TC_2.13 | TS_02 SIGN UP | To test the applications reaction when verification is complete | Access To the Mobile App | 1. Open App 2. Select Sign Up 3. input valid email 4. Input phone number 5. Click on Next 6. input valid BVN 7. Input date 8. Click on date 9. Select Next 10. Verify face ID 11. Input address 12. Click on next 13. Click the check box to attest 14. Click on Next | Not applicable |  | As Expected | Passed

## LOGIN
LOGIN
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result | Actual Result | Results | Comments
TC_3 | TS_03 LOGIN | To verify that users can login to users account with password | An active moniepoint account | 1. Open App 2. Click on Login 3. Input login details 4. Click login | Not applicable | User should be granted access to login | As Expected | Passed
TC_3.1 | TS_03 LOGIN | To verify that user can login with Biometrics | An active moniepoint account | 1. Open App 2. Click on Login 3. User face ID | Not applicable | User should be granted access to login | As Expected | Passed

## LOGOUT
LOGOUT
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result | Actual Result | Results | Comments
TC_4 | TS_04 LOGOUT | To verify that an account can be signed out | An active moniepoint account | 1. Open App 2. Click on Login 3. Input login details 4. Click login 5. Click on profile picture 6. Click on logout | Not applicable | The account should be loged out | As Expected | Passed
TC_4.1 | TS_04 LOGOUT | To verify that an account is signed out when inactive | An active moniepoint account | 1. Open App 2. Click on Login 3. Input login details 4. Click login | Not applicable | The account should be loged out | As Expected | Passed

## HOME
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result | Actual Result | Results | Comments
TC_5 | TS_05 HOME Account Number | To verify that account number can be copied |  | 1, Open App 2. Click on copy icon beside account number | None | Account number should be copied | As Expected | Passed
TC_5.1 | TS_05 HOME Account Number | To verify that money can be recieved | Have a Monie Point account number | 1. Copy Account Number 2. Transfer money from Other bank 3. Recieve money | Recieved N500 | Money sent should be recieved | As Expected | Passed
TC_5.2 | TS_05 HOME Transfer | To verify that money can be sent out | Have a funded account | 1. Open App 2. Click on Transfer 3. Input account number 4. Select bank 5. Click confirm 6. Input amount 7. select proceed 8. Select proceed 9. Input Pin | Not applicable | Money should be sent out | As Expected | Passed
TC_5.3 | TS_05 HOME Transfer | To Test if the application can automatically select the right bank |  | 1. Open App 2. Click on Transfer 3. Input account number 4. Select bank | Not applicable | The application should automatically select the right bank | The wrong bank was selected by the app | Failed
TC_5.4 | TS_05 HOME Transfer > History | To verify that Standard Statment can be Downloaded in excel | Has preformed transcations on account | 1. Open App 2. Click on Transfer 3. Click on the clock icon (History) 4. Click on the download icon 5. Select Standard Statement 6. click next 7. Select range 8. Click Excel 9. Click on next 10. Select Instant download 11. Click export | Not applicable | The history should be downloaded | A jason file was downloaded instead of an excel file | Failed | The History was not empty
TC_5.5 | TS_05 HOME Transfer > History | To verify that Standard Statement History can be Downloaded in pdf | Has preformed transcations on account | 1. Open App 2. Click on Transfer 3. Click on the clock icon (History) 4. Click on the download icon 5. Select Standard Statement 6. click next 7. Select range 8. Click pdf 9. Click on next 10. Select Instant download 11. Click export | Not applicable | The account statment should be downloaded | A jason file was downloaded instead of a pdf | Failed
TC_5.6 | TS_05 HOME Transfer > History | To verify that Extended Statement can be Downloaded in excel | Has preformed transcations on account | 1. Open App 2. Click on Transfer 3. Click on the clock icon (History) 4. Click on the download icon 5. Select Extentended Statement 6. click next 7. Select range 8. Click Excel 9. Click on next 10. Select Instant download 11. Click export | Not applicable | The account statment should be downloaded | A jason file was downloaded instead of an excel file | Failed
TC_5.7 | TS_05 HOME Transfer > History | To verify that Extended Statement can be Downloaded in pdf | Has preformed transcations on account | 1. Open App 2. Click on Transfer 3. Click on the clock icon (History) 4. Click on the download icon 5. Select Extentended Statement 6. click next 7. Select range 8. Click pdf 9. Click on next 10. Select Instant download 11. Click export | Not applicable | The account statment should be downloaded | A jason file was downloaded instead of a pdf | Failed
TC_5.8 | TS_05 HOME | To verify the display of the Home screen | Have preformed transcations on account | 1. Open app 2. Scroll down | Not applicable | The Home screen should be displayed properly | Money in and Money Out isn't displaying properly | Failed
TC_5.9 | TS_05 HOME Top-Up > Airtime | To verify that airtime can be purchased | Have a funded account | 1. Open App 2. Click on Top-Up 3. add phone number 4. Click proceed | Phone number: 08143854201 Provider: MTN | Airtime should be purchased | As Expected | Passed
TC_5.10 | TS_05 HOME Top-Up > Airtime | To verify the apps display of Airtime Details | Have a funded account | 1. Open App 2. Click on Top-Up 3. add phone number 4. Click proceed | Phone number: 08143854201 Provider: MTN | The service provider and Moniepoint account should be displayed | The service provider and Moniepoint account were not displayed | Failed
TC_5.11 | TS_05 HOME Top-Up > Airtime | To verify the apps display of the display of the transcation summary for Airtime purchase | Have a funded account | 1. Open App 2. Click on Top-Up 3. add phone number 4. Click proceed 5. Input amount 6. Click Proceed | Phone number: 08143854201 Provider: MTN | The service provider should be displayed in Beneficiary details | The service provider was not displayed in Beneficiary Details | Failed
TC_5.12 | TS_05 HOME Top-Up > Airtime | To verify the applications display when proceed is selected in transcation summary for Airtime purchase | Have a funded account | 1. Open App 2. Click on Top-Up 3. add phone number 4. Click proceed 5. Input amount 6. Click Proceed |  | The application should request the users pin | The application requested the users pin but the box's were displayed in read | Failed | A minor issue
TC_5.13 | TS_05 HOME Top-Up > Airtime | To verify the apps reaction when a glo number is inputed in airtime purchase | Have a funded account | 1. Open App 2. Click on Top-Up 3. add phone number | Phone number: 08111434727 Provider: GLO | The app should automatically select GLO as the network provider | The app selected MTN as the network provider | Failed
TC_5.14 | TS_05 HOME Top-Up > Airtime > Purchase Airtime > View Beneficiary | To verify that a saved beneficiary in airtime purchase can be viewed | Have a funded account | 1. Open App 2. Click on Top-Up 3. add phone number 4. Select add beneficiarie 5. Input beneficiary name 6. Click proceed 7. Input amount 8. Click Proceed 9. Click Proceed 10. Input pin 11. Click Confrim | Name: My Glo Phone number: 08111434727 Provider: Glo | Saved Beneficiary should be viewed | As Expected | Passed
TC_5.15 | TS_05 HOME Top-Up > Data | To verify that Data not saved in beneficiary can be purchased | Have a funded account | 1. Open App 2. Click on Top-Up 3. Selecetd Data 4. add phone number 5. Click proceed 6. Input amount 7. Click Proceed 8. Click Proceed 9. Input pin 10. Click Confrim | phone number: 07030673364 provider: MTN | Data should be purchased | Data was purchased but the number was saved to beneficiary | Failed
TC_5.16 | TS_05 HOME Top-Up > Data | To verify that data can be purchased when save as beneficiary is selected | Have a funded account | 1. Open App 2. Click on Top-Up 3. Selecetd Data 4. add phone number 5. Select add beneficiarie 6. Input beneficiary name 7. Click proceed 8. Input amount 9. Click Proceed 10. Click Proceed 11. Input pin 12. Click Confrim | Name: My MTN Phone number: 08143854201 Provider: MTN | Data should be purchased and the beneficiary should be saved | Data was purchased but the beneficiary was not save | Failed
TC_5.17 | TS_05 HOME Top-Up > Data | To verify the applications display when proceed is selected in transcation summary for Data purchase | Have a funded account | 1. Open App 2. Click on Top-Up 3. Select Data 4. add phone number 5. Click proceed 6. Input amount 7. Click Proceed | Name: My MTN Phone number: 08143854201 Provider: MTN | The application should request the users pin | The application requested the users pin but the box's were displayed in read | Failed | A minor issue
TC_5.18 | TS_05 HOME Top-Up > Data > History > Download | To verify that data purchase History can be downloaded | User has purchased Data | 1. Open App 2. Click on Top-Up 3. on Clock Icon 4. Select data 5. Click on the download Icon | Not applicable | The history should be downloaded | As Expected | Passed
TC_5.19 | TS_05 HOME Top-Up > Data > History > Download > View | To verify the display of the downloaded history | User has purchased Data | 1. Open App 2. Click on Top-Up 3. on Clock Icon 4. Select data 5. Click on the download Icon 6. Open File | Not applicable | The history should be displayed properly | No data was displayed | Failed
TC_5.20 | TS_05 HOME Top-Up > Airtime > History > Download > View | To verify that Airtime history can be downloaded | User has purchased Airtime | 1. Open App 2. Click on Top-Up 3. on Clock Icon 4. Click on the download icon | Not applicable | The history should be downloaded | "Failed Oops! It seems your history is empty" was displayed | Failed | The History was not empty
TC_5.21 | TS_05 HOME Notification | To verify the display of the notification icon | Has made transaction | 1. Open app 2. Make transcation 3. View notification icon | Not applicable | The pop up notification should be recieved and the number of notifications should be displayed on the icon | A pop up notification was recieved but the number of notifications were not displayed on the notification icon | Failed
TC_5.22 | TS_05 HOME Notification | To verify notifcations recieved can be viewed when the icon is selected | Has made transaction | 1. Open app 2. Make transcation 3. Click on notification icon | Not applicable | notifications recieved should be viewed | As Expected | Passed

## SETTINGS
SETTINGS
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result | Actual Result | Results | Comments
TC_6 | TS_06 SETTINGS Change Password | To verify that password can be changed | Active Account | 1. Open aApp 2. Click on profile picture 3. Select Change password 4. Input OTP 5. Input old and new password 6. Click confirm | Not applicable | An old password shouldn't be used | As Expected | Passed
TC_6.1 | TS_06 SETTINGS Change Password | To verify that old password can't be used | Active Account | 1. Open aApp 2. Click on profile picture 3. Select Change password 4. Input OTP 5. Input old password in both fileds 6. Click confirm | Not applicable | Password should be updated | As Expected | Passed
TC_6.2 | TS_06 SETTINGS Reset User PIN | To verify that a new pin can be created | Active Account | 1. Open aApp 2. Click on profile picture 3. Select Reset User Pin 4. Input OTP 5. Input new Pin | Not applicable | A new pin should be created | As Expected | Passed
TC_6.3 | TS_06 SETTINGS Reset User PIN | To verify that an old pin can't be used | Active Account | 1. Open aApp 2. Click on profile picture 3. Select Reset User Pin 4. Input OTP 5. Input old Pin | Not applicable | An old pin shouldn't be accepted | As Expected | Passed
TC_6.4 | TS_06 SETTINGS Hide Balance | To verify the functionality of the Hide balance | Active Account | 1. Open aApp 2. Click on profile picture 3. Turn on Hide balance | Not applicable | The balance should be hidden | As Expected | Passed
TC_6.5 | TS_06 SETTINGS Device Management | To verify the functionality of Device Management | Active Account | 1. Open aApp 2. Click on profile picture 3. Click on Device Management | Not applicable | Devices should be displayed | As Expected | Passed
TC_6.6 | TS_06 SETTINGS Beneficiaries | To verify functionality of beneficiary | Active Account | 1. Open aApp 2. Click on profile picture 3. Click on Beneficiaries | Not applicable | The beneficiaries should be displayed | Airtime purchase beneficiary only displayed numbers | Failed
TC_6.7 | TS_06 SETTINGS Beneficiaries | To verify that tranfer beneficiaries can be deleted | Active Account | 1. Open aApp 2. Click on profile picture 3. Click on Beneficiaries 4. Click on the Bin icon 5. Select Remove | Not applicable | The beneficiaries should be removed | As Expected | Passed
TC_6.8 | TS_06 SETTINGS Beneficiaries | To verify that airtime beneficiary can be removed | Active Account | 1. Open aApp 2. Click on profile picture 3. Click on Beneficiaries 4. Click on Airtime 5. Click on the Bin icon 6. Select Remove | Not applicable | The beneficiaries should be removed | An Error message was displayed "An Unexpected error occured while processing your request. Please try again later" | Failed

## CARDS
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result | Actual Result | Results | Comments
TC_9 | TS_09 CARDS | To verify the applications reaction when Get a debit card is selected | A Funded account | 1. Open app 2. Click on Cards 3. Click on get a debit card | Not applicable | The card type screen should be displayed | As Expected | Passed
TC_9.1 | TS_09 CARDS | To verify the applications reaction when Get A Physical Card is selected | A Funded account | 1. Open app 2. Click on Cards 3. Click on get a debit card 4. Click on get a physical card | Not applicable | The user should be directed to the card request screen | As Expected | Passed
TC_9.2 | TS_09 CARDS | To verify if card can be requested without delivery Area | A Funded account | 1. Open app 2. Click on Cards 3. Click on get a debit card 4. Click on get a physical card 5. Click on Next | Not applicable | The card shouldn't be requested | As Expected | Passed
TC_9.3 | TS_09 CARDS | To verify that card can be ordered | A Funded account | 1. Open app 2. Click on Cards 3. Click on get a debit card 4. Click on get a physical card 5. Click on Next 6. Set available time 7. Click on Next 8. Click on Request card | Not applicable | The card should be ordered | As Expected | Passed