## Defect Log
Description | Steps to reproduce | Expected result | Actual result | Screenshot | Bug/Suggestion
After onboarding, users are expected to enable biometrics. When a user clicks on enable button to set up biometrics, the application closes (stops working) | New user; - Onboard a new user - When you get to the biometric page, click on the enable button - Then, check the system response Existing user; - Input the user login details - Since the biometrics has not been set up, the set up page pops up - Click on the enable button - Then, check the system response | User should be able to set up and enable his/her biometrics. | The system stops working. | https://anyimage.io/storage/uploads/b55706a894fbc30781c14b6c61f2f6d5 | BUG
The spending trend on the dashboard isn't showing the transaction flow has expected i.e. inflow and outflow. | - Login to the system - Initiate transactions (inflow and outflow) - Then, check the spending trend on the dashboard if it captures the transactions | The spending trend is expected to capture the inflow and outflow of the user | It is not capturing the transactions. It is still showing 0 whereas transactions have been carried out on the account. | https://anyimage.io/storage/uploads/a9ecb2d95e4ea3a102757a5e8b75db80 | BUG
When a user intends to purchase airtime, the transaction pin input box are displaying red (which sends error message) even when the pin has not been typed in. | - Click on top up on the dashboard - Input the number - Select the network provider - Enter or select amount - Click on proceed - Confirm the number and proceed - Then, check the UI representation of the input box for the transaction pin | The input box shouldn't be red as it sends an error message to the user. | The input box is displaying red. | https://anyimage.io/storage/uploads/8e9a01901200464f9988748a28a3730f | BUG
When a user tries to confirm the number after the number validation by going back to the initial page, the user is stalked as the network provider page doesn't show up again. | - Click on top up on the dashboard - Input the number - Click on the back button - Afterwards, click done without changing the number - Then, check the system response | Upon clicking done, user should be able to proceed to the network provider's page. | The user is stalked and cannot proceed except the number is typed in again. |  | BUG
When users input wrong transaction pin, they should be able to retry without starting the flow all over again. | - Initiate any form of transaction (airtime purchase/transfer) - Navigate to the transaction pin page - Input the wrong pin | User should be able to retry without starting the flow all over again. | User is taken back to the beginning of the flow. |  | SUGGESTION
Web chat uploaded documents are not clearing. | - Navigate to the help & suppot page - Click on live web chat - Upload a document - Click on back and go back to the dashboard - Then, proceed to the live web chat page again - The uploads are still showing | Since it is a live web chat, the chat should be cleared or dismissed after some minutes. Suggestion: users should be able to delete uploaded documents/pictures. This will be useful for mistake during uploads. | The uploads are still visible in the live web chat page even hours after upload. The pictures were uploaded around 1:11 pm and they are still in the chat till 8pm. | https://anyimage.io/storage/uploads/d69eb492297b58886ca1d597d1ee386d | BUG
When user clicks on privacy policy during onboarding to view the content, they can see the terms and conditions instead of the privacy policy. | - | - | - |  | BUG