## INFO
Project Name | Moniepoint Beta Test
Designed By | Daniel Oyebode
Device | Mobile
Operating System | iOS
Date | 5th of September, 2023
Account Info | 5362204380 ¦ Moniepoint MFB

## ISSUES LOG
S/N | Use Case | Description | Expected Result | Actual Result | Steps to Recreate | Severity | Screenshot
1 | Login | There's no way for the user to navigate to the landing page | A back button or a "Signup" label link should be added to the "Login" screen for users to be able to create account | There's no "Back Button" or "Signup" label link on the login screen | 1. Launch the Moniepoint mobile application 2. Click the login button | Medium | https://www.loom.com/share/d598957848574760b2f9bd59f5fff14f
2 | Sign up | The user is able to complete account setup with an expired otp | The otp should be validated and user prompted to generate another OTP | The user is able to successfully create an account with an expired OTP | 1. Launch the Moniepoint mobile application 2. Click the signup button 3. Provide valid details 4. Input an exired OTP in the OTP field | Critical |  | `
3 | Dashboard / Moniepoint Coins | The error message "An Error Occured" is returned when the user clicks the "Start Playing" button | The user should be directed to the appropriate page when the "Start Playing" button is clicked | An error message is displayed when the user clicks the "Start Playing" button | 1. Click the "Play now" button 2. Click the "Start Playing" button | High | https://www.loom.com/share/8b55a2db82124934b78bc3bfec57583e
4 | Dashboard | The spending trend (This Week) isn't updated when a credit trancation occures on the account | When a credit occurs on an account, the spending trend section should be updated | The spending trend section of the dashboard isn't updated when a credit transaction occurs | 1. Launch the Moniepoint application 2. Login to Moniepoint 3. Inspect the Spending Trending section of the dashboard | Medium | https://www.loom.com/share/219efcb796594d519477b0acb397eea3
5 | Dashboard | The spending trend (This Month) isn't updated when a credit trancation occures on the account | When a credit occurs on an account, the spending trend section should be updated | The spending trend section of the dashboard isn't updated when a credit transaction occurs | 1. Launch the Moniepoint application 2. Login to Moniepoint 3. Inspect the Spending Trending section of the dashboard | Medium | https://www.loom.com/share/219efcb796594d519477b0acb397eea3
6 | Login | The login endpoint is a bit unstable The user is unable to login at certain points and a login success email notification is sent to the user | The user should be able to login successfully with valid credentials | Different errors are returned when the user attempts to login e.g Gateway timeout, Connection timeout... | 1. Launch the Moniepoint mobile 2. Input valid username 3. Input a valid password 4. Click the Login button | Critical | https://www.loom.com/share/ff3b0f6543fd4f84b99fbcdfcce1708f
7 | Statement Report | The message "No record is found" when the user generates a statement report. Note that a credit transaction has occured on the account | All transactions carried out should be displayed in the "Statement Report" file | The message "No record is found" when the user generates a statement report. | 1. Launch the Moniepoint application 2. Login with vaid credentials 3. Click the "See more" label link in the "Recet Transaction" section of the Dashboard 4. Click the "Download" icon 5. Select Statement Type (Extended & Standard Statement) 6. Select a date range 7. Select the file type (Excel & PDF) 8. Click the "Next" button 9. Click the "Instant Download" radio button 10. Click the "Export" button 11. Click the "Open File" button | High | https://www.loom.com/share/d9bcd5d4ccb84f348109f1661c6f09e5
8 | Filter Transactions | When the user applies the "Last Month" filter, the appropriate data isn't returned Note that "Last Quarter" and "Last Year" display the same behaviour | All transactions carried out in the previous month alone should be returned | Recent transactions are displayed when the user applies the last month filter | 1. Launch the Moniepoint application 2. Login with vaid credentials 3. Click the "See more" label link in the "Recet Transaction" section of the Dashboard 4. Click the "Filter" icon 5. Apply the "Last Month" filter | Medium | https://www.loom.com/share/ac9e281032884d2084ca48464e41f594
9 | Top-up / Beneficiaries | The application isn't checking to see if a beneficiary exists already The user is able to add the same beneficiary multiple times | Once a number as been added as a beneficiary, then the option to addd the same number to beneficiary should either be greyed out or removed completely | The user is able to add the same number to beneficiary twice Note that the previous name isn't overwritten | 1. Launch the Moniepoint application 2. Login with vaid credentials 3. Click the "Topup" button 4. Input mobile number 5. Add a number that's already a beneficiary | Medium | https://www.loom.com/share/8d4afb154f7c429db61c8c49b976a797

## RECOMMENDATION
S/N | Use Case | Recommendation
1 | Top-up | Since the user sees a pending status after an airtime purchase, then a status should be added to transaction details to show if the airtime purchase was successful or not