## Sheet1
NAME: Gambo Usman Yusuf |  | ACC NUMBER: 5358696463
DEVICE: Android ( Inifinix hot 10)
Date | Feature/page | Description | Repro steps | Screenshot URL | Issue Type | Priority | PM's/Dev's Approval / Comments | ReTest Status | Number of Iteration
2023-02-09 | Help and support>Contact Page | User can not access the Facebook social media page, user gets this error message: "Webpage not available" | 1.Navigate to the profile details page 2. Click Help and support tab 3. Scroll down and click on the facebook icon | https://drive.google.com/file/d/1V_PYQR3fR4Akg1DTSIfnTigS80smm7Sm/view?usp=drive_link | BUG | LOW
| Privacy Policy | The privacy document is the same as that of TERms and conditons |  | https://drive.google.com/file/d/1VUg_PpzCWBgPvumeikMFgjupmQizRqm8/view?usp=drive_link | BUG | LOW
| Forget username> Username recovery | The user is unable to recover the username from their registered phone number, the error message received was " no username attached to this phone number, and the user was able to sign in to the APP with a username | 1. Navigate to the login page 2. Click forget username or Passwoerd link 3. Select forget username 4. dial the recovery code from your registered phone number | https://drive.google.com/file/d/1VSiEllDvwe2MMxEKX3jf3vM4xfaSJoQN/view?usp=drive_link | BUG | HIGH
| Bill payment>Cable TV>GOTV | Fetch smart card info request failed | 1. Click Pay Bills tab 2. Select Cable TV 3. Select Go TV 4. Select plan 5. enter IUC number 6. click to get beneficiaery detail | https://drive.google.com/file/d/1Vh6sHgvGJkzRq24YqvqsB5BR9OUXf1vi/view?usp=drive_link | BUG | HIGH
| Bill payment>Cable TV>DSTV | Fetch smart card info request failed | 1. Click Pay Bills tab 2. Select Cable TV 3. Select DSTV 4. Select plan 5. enter Smart card number 6. click to get beneficiaery detail | https://drive.google.com/file/d/1Vh6sHgvGJkzRq24YqvqsB5BR9OUXf1vi/view?usp=drive_link | BUG | HIGH
| Bill payment>Cable TV>Startime | Fetch smart card info request failed | 1. Click Pay Bills tab 2. Select Cable TV 3. Select Startime 4. Select plan 5. enter Smart card number 6. click to get beneficiaery detail | https://drive.google.com/file/d/1Vh6sHgvGJkzRq24YqvqsB5BR9OUXf1vi/view?usp=drive_link | BUG | HIGH
| Statement Report | downloaded sucessfully, but user can not open the file | 1.Navigate to the transaction history page 2. Click the download icon 3. Select statement type 4. Select date range 5. select file type 6. Select instant download 7. click the export button | https://drive.google.com/file/d/1Vzc0BSBo4Z9zRtCMkNPZDCfVy9iQl9f8/view?usp=drive_link | BUG | HIGH
| Transfer>Credit alert receipt | The credit alert receive by the beneficiary contains "Rolez microfinance Bank" as the Bank name | 1. make a transfer 2. view the receipt of the credit alert | https://drive.google.com/file/d/1W9iG3uzlBCzjvx4GBHjnUc-Nt5ct7KOP/view?usp=drivesdk | BUG
| FAQs>I have not received the OTP | The text, "resend OPT via SMS" should be corrected to "resend OTP via SMS" | 1. Navigate to the FAQ Page | https://drive.google.com/file/d/1WkFHtSi4EvZpEbSiIvEVk_XFRn9uIm2r/view?usp=drivesdk | Textual correction